## Sheet1
Data tasks | Sub Tasks | Description | Priority | ETA | Resources | Owner | Status | Trend
APA WS | WS | Web Scrape to create a data base | H | 2019-09-21 | https://www.austinpetsalive.org/impact | Edgar | Not started
| Plotting | New plot for APA data | L | 2019-09-21 | https://animejs.com/ | JP | Not started
Stray Mapping | Heat Map | Use the data set to create a heat map | H | 2019-09-21 | https://data.austintexas.gov/Health-and-Community-Services/Austin-Animal-Center-Stray-Map/kz4x-q9k5 | Aziz | Not started
Animal center outcome | Dog Imaging Pandas | Filter by dog and create plots that shows outcome type vs diferent categories unsing pandas | H | 2019-09-17 | https://data.austintexas.gov/Health-and-Community-Services/Austin-Animal-Center-Outcomes/9t4d-g238 | Ufuk | Not started
| sent the data frame to JS using Flask |  | H | 2019-09-19 |  |  | Not started
| Create the plots using JS |  | H | 2019-09-21 |  | JP | Not started
Create a repo |  |  | HH | 2019-09-14 |  |  | Not started